## Schedule
WEEK OF JUNE 23, 2025
CREW LEADS: CARLOS ARROYO, CRUZ CORTEZ, FRANCISCO GUTIERREZ, JOSE DUARTE, JULIAN BAUTISTA, MIGUEL MURILLO, VICTOR CORDOVA, VICTOR SORIANO, VICTOR SUAREZ
PROJECT | WORK | CONCRETE | MONDAY 06/23 | TUESDAY 06/24 | WEDNESDAY 06/25 | THURSDAY 06/26 | FRIDAY 06/27 | SATURDAY 06/28 | SUNDAY 06/29 | NOTES
WEEK OF JUNE 30, 2025
CREW LEADS: CARLOS ARROYO, CRUZ CORTEZ, FRANCISCO GUTIERREZ, JOSE DUARTE, JULIAN BAUTISTA, MIGUEL MURILLO, VICTOR CORDOVA, VICTOR SORIANO, VICTOR SUAREZ
PROJECT | WORK | CONCRETE | MONDAY 06/30 | TUESDAY 07/01 | WEDNESDAY 07/02 | THURSDAY 07/03 | FRIDAY 07/04 | SATURDAY 07/05 | SUNDAY 07/06 | NOTES
CWM04066 - CONSTRUCTION OF A ROUNDABOUT ON SR 18 @ JACKSON LAKE RD/SNAPPING SHOALS ROAD | test | CONCRETE ENTERPRISES |  | Carlos Arroyo (10:30 am, 10+) | NEED CREW (10:30 am, 10+) | NEED CREW (10:30 am, 10+) | 4TH OF JULY |  |  | test
ERS05031 - SR 59 BRIDGE REPLACEMENT | Prueba Lead | ARGOS |  | Cruz Cortez (10:00 am, 5+) | NEED CREW (10:00 am, 5+) | NEED CREW (10:00 am, 5+) | 4TH OF JULY | NEED CREW (10:00 am, 5+) | NEED CREW (10:00 am, 5+)
ERS05070 - Hall, White Sulphur Road | Jenkis | MORGAN |  | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+ | 4TH OF JULY
PC25032 - SR 15 | Deploy | FOWLER |  | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+ | 4TH OF JULY