## Invoice
INVOICE
C&G CONCRETE CONSTRUCTION CO., INC.
[7 empty] | Date | Invoice #
|  | 1445 Willingham Dr | Office: 404-684-5963 |  |  |  | 12/23/2024 | 2
|  | East Point, Ga. 30344 | Fax: 404-684-5201
|  | cag@cagconcrete.com | bids@cagconcrete.com
| Bill To: | [5 empty] | Start Date | End Date
| Contractor's Name: |  | Inspector's Name: |  |  |  | 12/01/2024 | 12/31/2024
| Disrupsoft |  | Carlos Magill
| Contractor's Phone Number: |  | Inspector Cell Number:
| (653)289-6532 |  | (678)558-2565
Contact Name
| Email/No. |  | gill@arersnl.com
| PROJECT LOCATION: |  |  |  | PROJECT # | 0009003
| PROJECT NAME: | Houston Texas |  |  | PO NUMBER #
C&G PO#
Notes:
Item #: | DESCRIPTION |  |  | UNIT | CONTRACT QTY | UNIT PRICE | CONTRACT AMOUNT | QUANTITY FROM PREVIOUS APPLICATION | QUANTITY THIS PERIOD | TOTAL QAUNTITY COMPLETED | AMOUNT THIS PERIOD | TOTAL AMOUNT (TODATE)
1 | CONC CURB & GUTTEER 8INX30IN TP2 |  |  | LF | 1500 | 16.5 | 24750 | 0 |  | 0 | 0 | 0
2 | CONC SIDEWALK 8IN |  |  | SY | 2000 | 63 | 126000 | 0 |  | 0 | 0 | 0
3 | Cubic Yards of Concrete |  |  | CY | 1600 | 150 | 240000 | 0 |  | 0 | 0 | 0
4 | CONCRETE V GUTTER |  |  | LF | 2500 | 25 | 62500 | 0 |  | 0 | 0 | 0
5 | CONC CURB & GUTTEER 8INX30IN TP7 |  |  | LF | 2500 | 16.5 | 41250 | 0 |  | 0 | 0 | 0
6 | CONC DRIVEWAY 8IN |  |  | SY | 5000 | 70 | 350000 | 0 |  | 0 | 0 | 0
[6 empty] | TOTAL | 844500 |  | Total Completed |  | 0 | 0