## Invoice
INVOICE
C&G CONCRETE CONSTRUCTION CO., INC.
[7 empty] | Date | Invoice #
|  | 1445 Willingham Dr | Office: 404-684-5963 |  |  |  | 02/16/2025 | 1
|  | East Point, Ga. 30344 | Fax: 404-684-5201
|  | cag@cagconcrete.com | bids@cagconcrete.com
| Bill To: | [5 empty] | Start Date | End Date
| Contractor's Name: |  | Inspector's Name: |  |  |  | 02/01/2025 | 02/28/2025
| CONTRACTOR, INC |  | Carlos Magill
| Contractor's Phone Number: |  | Inspector Cell Number:
| (618)985-7850 |  | (678)558-2565
Contact Name
| Email/No. |  | gill@arersnl.com
| PROJECT LOCATION: | Miami |  |  | PROJECT #
| PROJECT NAME: | FL MIAMI |  |  | PO NUMBER # | M345435435
[5 empty] | C&G PO# | 0009002
Notes: | test
Item #: | DESCRIPTION |  |  | UNIT | CONTRACT QTY | UNIT PRICE | CONTRACT AMOUNT | QUANTITY FROM PREVIOUS APPLICATION | QUANTITY THIS PERIOD | TOTAL QAUNTITY COMPLETED | AMOUNT THIS PERIOD | TOTAL AMOUNT (TODATE)
1 | CONC DRIVEWAY 8IN |  |  | SY | 50 | 160 | 8000 | 0 | 10 | 10 | 1600 | 1600
2 | CONC CURB & GUTTEER 8INX30IN TP2 |  |  | LF | 60 | 200 | 12000 | 0 | 10 | 10 | 2000 | 2000
3 | CONC CURB & GUTTEER 8INX30IN TP7 |  |  | LF | 50 | 300 | 15000 | 0 | 10 | 10 | 3000 | 3000
[6 empty] | TOTAL | 35000 |  | Total Completed |  | 6600 | 6600