## Client Invoice Export
INVOICE
|  | C&G CONCRETE CONSTRUCTION CO., INC. |  |  |  | BILL TO: |  |  |  |  | PROJECT LOCATION: |  | Gwinnett |  |  | Date | Invoice #
[6 empty] | Contractor's Name: |  | Inspector's Name: |  |  | PROJECT NAME: |  | Lakeview Road Bridge |  |  | 02/21/2026 | 1
|  | 1258 Willingham Dr | Office: 404-254-2017 |  |  | E.R. SNELL CONTRACTOR, INC. |  | Empleado_Prueba_13 | [7 empty] | Start Date | End Date
|  | East Point, Ga. 5025 | Fax: 404-589-5896 |  |  | Contractor's Phone Number: |  | Inspector Cell Number: |  |  | PROJECT # |  | F-1251-01 & M-1238-31 |  |  | 09/01/2025 | 09/30/2025
|  | data_t@concrete.com | data_t@concrete.com | [7 empty] | PO NUMBER # |  | 50445
[6 empty] | Contact Name |  |  |  |  | C&G PO# |  | ERS05071
Email/No.
Notes:
Item #: | DESCRIPTION |  |  | UNIT | UNIT PRICE | CONTRACT QTY | CONTRACT AMOUNT | TOTAL QTY BTD | TOTAL AMOUNT BTD | PREVIOUS BILL QTY | PREVIOUS BILL AMOUNT | PENDING QTY (BTD) | PENDING BALANCE (BTD) | QTY THIS PERIOD | AMOUNT THIS PERIOD | BILLED QTY THIS PERIOD | BILLED AMOUNT THIS PERIOD
1 | CONC DRIVEWAY, 6 IN |  |  | SY | 87 | 48 | 4176 | 25 | 2175 | 0 | 0 | 0 | 0 | 25 | 2175 | 25 | 2175
2 | CONC SIDEWALK, 4 IN |  |  | SY | 58 | 1 | 58 | 889.63 | 51598.54 | 0 | 0 | 0 | 0 | 889.63 | 51598.54 | 889.63 | 51598.54
3 | CLASS B CONC, BASE OR PVMT WIDENING |  |  | CY | 386 | 16 | 6176 | 40 | 15440 | 0 | 0 | 0 | 0 | 40 | 15440 | 40 | 15440
4 | CONC CATCH BASIN TOP & THROAT |  |  | EA | 2200 | 17 | 37400 | 35.5 | 78100 | 0 | 0 | 0 | 0 | 35.5 | 78100 | 35.5 | 78100
5 | CONC DROP INLET |  |  | EA | 800 | 2 | 1600 | 22 | 17600 | 0 | 0 | 0 | 0 | 22 | 17600 | 22 | 17600
6 | CONC CURB & GUTTER 8 IN X 30 IN TP 2 |  |  | LF | 36 | 2810 | 101160 | 2506 | 90216 | 0 | 0 | 0 | 0 | 2506 | 90216 | 2506 | 90216
7 | ADJUST MANHOLE TO GRADE |  |  | EA | 20 | 500 | 10000 | 50 | 1000 | 0 | 0 | 0 | 0 | 50 | 1000 | 50 | 1000
8 | 6 IN HEADER CURB |  |  | LF | 20 | 523 | 10460 | 12 | 240 | 0 | 0 | 0 | 0 | 12 | 240 | 12 | 240
9 | ADJUST WATER VALVE TO GRADE |  |  | EA | 10 | 125 | 1250 | 32 | 320 | 0 | 0 | 0 | 0 | 32 | 320 | 32 | 320
10 | BOND |  |  | LS | -1823.75 | 1 | -1823.75 | 1 | -1823.75 | 0 | 0 | 0 | 0 | 1 | -1823.75 | 1 | -1823.75
11 | 4 IN SIDEWALK $5 LOT |  |  | SY | 10 | 150 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 4 INCH V-GUTTER |  |  | LF | 10 | 120 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 6 IN DUMPSTER PAD (DOES NOT INCLUDE CATCH BASIN) |  |  | SF | 10 | 500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 6' CONCRETE SIDEWALK |  |  | SF | 12 | 250 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHANGE ORDER IN OCTOBER 2025
15 | SIDEWALK ON BRIDGE 10 IN W/REINF |  |  | SY | 124 | 5 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | TOTAL CONTRACT AMOUNT: | 181776.25 | TOTAL AMOUNT BTD: | 254865.79 | TOTAL PREVIOUS BILL AMT: | 0 | TOTAL PENDING BALANCE: | 0 | TOTAL AMT THIS PERIOD: | 254865.79 | TOTAL BILLED AMOUNT: | 254865.79
[8 empty] | LESS RETAINAGE | 0 | [6 empty] | CURRENT RETAINAGE @ 10.00% | 0
[8 empty] | AMOUNT EARNED LESS RETAINAGE: | 254865.79 | [6 empty] | CURRENT AMOUNT DUE: | 254865.79