## Client Invoice Export
INVOICE
|  | C&G CONCRETE CONSTRUCTION CO., INC. |  |  |  | BILL TO: |  |  |  |  | PROJECT LOCATION: |  | BACON |  |  | Date | Invoice #
[6 empty] | Contractor's Name: |  | Inspector's Name: |  |  | PROJECT NAME: |  | TESTING001 |  |  | 02/07/2026 | 2
|  | 1258 Willingham Dr | Office: 404-254-2017 |  |  | TEST TEST CO. |  | Empleado_Prueba_48 | [7 empty] | Start Date | End Date
|  | East Point, Ga. 5025 | Fax: 404-589-5896 |  |  | Contractor's Phone Number: |  | Inspector Cell Number: |  |  | PROJECT # |  | 1233455 |  |  | 10/01/2025 | 10/31/2025
|  | data_t@concrete.com | data_t@concrete.com | [7 empty] | PO NUMBER # |  | WE34
[6 empty] | Contact Name |  |  |  |  | C&G PO# |  | TT0001
Email/No.
Notes:
Item #: | DESCRIPTION |  |  | UNIT | UNIT PRICE | CONTRACT QTY | CONTRACT AMOUNT | TOTAL QTY BTD | TOTAL AMOUNT BTD | PREVIOUS BILL QTY | PREVIOUS BILL AMOUNT | PENDING QTY (BTD) | PENDING BALANCE (BTD) | QTY THIS PERIOD | AMOUNT THIS PERIOD | BILLED QTY THIS PERIOD | BILLED AMOUNT THIS PERIOD
1 | 12 IN HEADER CURB |  |  | LF | 36 | 2 | 72 | 200 | 7200 | 100 | 3600 | 120 | 4320 | 100 | 3600 | 120 | 4320
2 | BAR REINF STEEL |  |  | LBS | 10 | 15 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | ADA RAMP TP A |  |  | EA | 1 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 6 IN BRIDGE SIDEWALK & DRIVEWAYS |  |  | SF | 12 | 12 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHANGE ORDER IN AUGUST 2025
5 | 18" C&G $5 LOT |  |  | LF | 2 | 49 | 98 | 400 | 800 | 200 | 400 | 100 | 200 | 200 | 400 | 200 | 400
CHANGE ORDER IN NOVEMBER 2025
6 | 24 ROLLBACK CURB AND GUTTER REPLACEMENT ( 6-10 VAR |  |  | LF | 3 | 30 | 90 | 600 | 1800 | 300 | 900 | 300 | 900 | 300 | 900 | 300 | 900
7 | 8' CONCRETE SIDEWALK |  |  | SY | 4 | 70 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHANGE ORDER IN DECEMBER 2025
8 | C&G 8x30 IN, TP 2 |  |  | LF | 28 | 360 | 10080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 12 IN HEADER CURB |  |  | LF | 22 | 12 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | AMENDMENT |  |  | EA | 50 | 50 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHANGE ORDER IN APRIL 2026
11 | 4" CONCRETE PAVEMENT FOR SIDEWALK |  |  | LF | 2 | 90 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | TOTAL CONTRACT AMOUNT: | 13870 | TOTAL AMOUNT BTD: | 9800 | TOTAL PREVIOUS BILL AMT: | 4900 | TOTAL PENDING BALANCE: | 5420 | TOTAL AMT THIS PERIOD: | 4900 | TOTAL BILLED AMOUNT: | 5620
[8 empty] | LESS RETAINAGE | 576 | [6 empty] | CURRENT RETAINAGE @ 5.00% | 216
[8 empty] | AMOUNT EARNED LESS RETAINAGE: | 9224 | [6 empty] | CURRENT AMOUNT DUE: | 5404