## Invoice
INVOICE
C&G CONCRETE CONSTRUCTION CO., INC.
[7 empty] | Date | Invoice #
|  | 1445 Willingham Dr | Office: 404-684-5963 |  |  |  | 12/20/2024 | 1
|  | East Point, Ga. 30344 | Fax: 404-684-5201
|  | cag@cagconcrete.com | bids@cagconcrete.com
| Bill To: | [5 empty] | Start Date | End Date
| Contractor's Name: |  | Inspector's Name: |  |  |  | 08/01/2024 | 08/31/2024
| CONTRACTOR, INC |  | Carlos Magill
| Contractor's Phone Number: |  | Inspector Cell Number:
| (618)985-7850 |  | (678)558-2565
Contact Name
| Email/No. |  | gill@arersnl.com
| PROJECT LOCATION: | FL MIAMI |  |  | PROJECT # | 0009002
| PROJECT NAME: | FL MIAMI |  |  | PO NUMBER # | 896532
[5 empty] | C&G PO# | 896532
Notes:
Item #: | DESCRIPTION |  |  | UNIT | CONTRACT QTY | UNIT PRICE | CONTRACT AMOUNT | QUANTITY FROM PREVIOUS APPLICATION | QUANTITY THIS PERIOD | TOTAL QAUNTITY COMPLETED | AMOUNT THIS PERIOD | TOTAL AMOUNT (TODATE)
1 | CONC DRIVEWAY 8IN |  |  | SY | 50 | 160 | 8000 |  | 40 | 40 | 6400 | 6400
2 | CONC CURB & GUTTEER 8INX30IN TP2 |  |  | LF | 60 | 200 | 12000 |  | 50 | 50 | 10000 | 10000
3 | CONC CURB & GUTTEER 8INX30IN TP7 |  |  | LF | 50 | 300 | 15000 |  | 30 | 30 | 9000 | 9000
4 | CONC DRIVEWAY 8IN |  |  | SY | 50 | 160 | 8000 | 40 | 40 | 80 | 6400 | 12800
5 | CONC CURB & GUTTEER 8INX30IN TP2 |  |  | LF | 60 | 200 | 12000 | 50 | 50 | 100 | 10000 | 20000
6 | CONC CURB & GUTTEER 8INX30IN TP7 |  |  | LF | 50 | 300 | 15000 | 30 | 1 | 31 | 300 | 9300
[6 empty] | TOTAL | 70000 |  | Total Completed |  | 42100 | 67500