## Schedule
WEEK OF MAY 26, 2025
CREW LEADS: CARLOS ARROYO, CRUZ CORTEZ, FRANCISCO GUTIERREZ, JOSE DUARTE, JULIAN BAUTISTA, MIGUEL MURILLO, VICTOR CORDOVA, VICTOR SORIANO, VICTOR SUAREZ
PROJECT | WORK | CONCRETE | MONDAY 05/26 | TUESDAY 05/27 | WEDNESDAY 05/28 | THURSDAY 05/29 | FRIDAY 05/30 | SATURDAY 05/31 | SUNDAY 06/01 | NOTES
BP02021 - SR 13 RESURFACING | Test | ERNST | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+
COLD40007 - DAMASCUS ROAD AT UPPER BETHANT ROAD | Test | WAYNESBORO | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+ | NEED CREW 0+
CWM04066 - CONSTRUCTION OF A ROUNDABOUT ON SR 18 @ JACKSON LAKE RD/SNAPPING SHOALS ROAD | test | CONCRETE ENTERPRISES | [6 empty] | NEED CREW (10:30 am, 10+) | test
ERS05031 - SR 59 BRIDGE REPLACEMENT | Prueba | ARG | [6 empty] | NEED CREW 10+ | test
WEEK OF JUNE 2, 2025
CREW LEADS: CARLOS ARROYO, CRUZ CORTEZ, FRANCISCO GUTIERREZ, JOSE DUARTE, JULIAN BAUTISTA, MIGUEL MURILLO, VICTOR CORDOVA, VICTOR SORIANO, VICTOR SUAREZ
PROJECT | WORK | CONCRETE | MONDAY 06/02 | TUESDAY 06/03 | WEDNESDAY 06/04 | THURSDAY 06/05 | FRIDAY 06/06 | SATURDAY 06/07 | SUNDAY 06/08 | NOTES
CWM04066 - CONSTRUCTION OF A ROUNDABOUT ON SR 18 @ JACKSON LAKE RD/SNAPPING SHOALS ROAD | test | CONCRETE ENTERPRISES | NEED CREW (10:30 am, 10+) | NEED CREW (10:30 am, 10+) | NEED CREW (10:30 am, 10+) | NEED CREW (10:30 am, 10+) | NEED CREW (10:30 am, 10+) | NEED CREW (10:30 am, 10+) |  | test
ERS05031 - SR 59 BRIDGE REPLACEMENT | Prueba | ARG | NEED CREW 10+ | NEED CREW 10+ | NEED CREW 10+ | NEED CREW 10+ | NEED CREW 10+ | NEED CREW 10+ |  | test