## Schedule
WEEK OF JULY 28, 2025
CREW LEADS: CARLOS ARROYO, CRUZ CORTEZ, FRANCISCO GUTIERREZ, JOSE DUARTE, JULIAN BAUTISTA, LUIS G.CORDOVA, MIGUEL MURILLO, VICTOR CORDOVA, VICTOR SORIANO, GERARDO ALVARADO
PROJECT | WORK | CONCRETE | MONDAY 07/28 | TUESDAY 07/29 | WEDNESDAY 07/30 | THURSDAY 07/31 | FRIDAY 08/01 | SATURDAY 08/02 | SUNDAY 08/03 | NOTES
EDG45000 - LAURENS | Prueba | BASIC | [6 empty] | Abram Sanchez (12:30 am, 10+)
PC25032 - GREENE | Prueba | BASIC |  |  |  |  | Abram Sanchez Alfredo Chegue (1:00 am, 10+) | Abram Sanchez Alfredo Chegue (1:00 am, 10+) | Abram Sanchez Alfredo Chegue (1:00 am, 10+)
WEEK OF AUGUST 4, 2025
CREW LEADS: CARLOS ARROYO, CRUZ CORTEZ, FRANCISCO GUTIERREZ, JOSE DUARTE, JULIAN BAUTISTA, LUIS G.CORDOVA, MIGUEL MURILLO, VICTOR CORDOVA, VICTOR SORIANO, GERARDO ALVARADO
PROJECT | WORK | CONCRETE | MONDAY 08/04 | TUESDAY 08/05 | WEDNESDAY 08/06 | THURSDAY 08/07 | FRIDAY 08/08 | SATURDAY 08/09 | SUNDAY 08/10 | NOTES
EDG45000 - LAURENS | Prueba | BASIC | Abram Sanchez (12:30 am, 10+) | Abram Sanchez (12:30 am, 10+) | Abram Sanchez (12:30 am, 10+) | Abram Sanchez (12:30 am, 10+) | Abram Sanchez (12:30 am, 10+) | Abram Sanchez (12:30 am, 10+)
PC25032 - GREENE | Prueba | BASIC | Abram Sanchez Alfredo Chegue (1:00 am, 10+) | Abram Sanchez Alfredo Chegue (1:00 am, 10+) | Abram Sanchez Alfredo Chegue (1:00 am, 10+) | Abram Sanchez Alfredo Chegue (1:00 am, 10+) | Abram Sanchez Alfredo Chegue (1:00 am, 10+) |  | Abram Sanchez Alfredo Chegue (1:00 am, 10+)